## Action Plan Template
Bristol SU Equalities Action Plan
| Barrier to Participation | Action(s) | Who is responsible? | When will it be done by? | Progress
1 | Fear of sexual harassment | Introduce a zero-tolerance policy on sexual harassment and inform members about it | Equality Officer | 2024-03-01 | Society-wide email to be sent py President, website(s) to be updated
|  | Make members aware of the SU's Code of Conduct and expectations around behaviour | Equality Officer | 2024-03-01 | Society-wide email to be sent py President, website(s) to be updated
|  | Only run socials at venues where sexual harassment is uncommon | Social Secretary | 2024-03-01 | Done
2 | Lack of role models | Create promotional materials featuring students/role models with different characteristics | Equality Officer | 2024-09-01 | Promotional materials already demonstrate some diversity, could be improved
|  | Celebrate a diverse selection of role models on social media | Equality Officer, Social Media Manager | 2025-01-01 | Celebrated International Womens Day on social media last year; some diversity; could be improved
|  | Invite a female/BME trainer/speaker to run a session | All of committee | 2024-03-01 | Panel event planned for 20th Feb on EDI in outdoor sport with a variety of speakers
|  | Encourage students from different backgrounds to run for committee positions | President, All of committee | 2024-10-01 | Keep in mind for AGM 9th March and pre-AGM
3 | Lack of alcohol-free events, especially socials
|  | Provide alcohol-free events/socials | Social Secretary | 2024-10-01 | Alcohol-free talks series in progress
e.g. bowling, film night, mini golf, board games, scavenger hunt, picnic, talks